Randolph Public Schools

Accelerated

Improvement Plan

2014-2015

# Section 1: Summary of Key Issues and Strategic Objectives

BACKGROUND The Randolph Public Schools has been operating with an Accelerated Improvement Plan for the past three years. Having been designated a level four district in 2010, the district embarked on a plan of continuous improvement targeted at addressing areas of weakness as identified in the initial ESE District Review. This year’s plan builds upon data showing changes in student learning outcomes, observed changes in adult behavior, lessons learned from prior years, and the district’s overall progress toward meeting the objectives of prior plans. For 2015, using the continuous acts of planning, training, implementing, measuring, and analyzing progress, the district has built a series of initiatives and associated activities designed at addressing the needs cited in the initial district review and ESE’s subsequent quarterly and annual reviews of the district’s progress. The objectives of the 2015 AIP and rationale for their continuance are: Through the objective of “Ensuring success for all students through high quality teaching and learning,” the district is addressing the findings of: The need to focus on the literacy skills of students, which are below state average. The need to address the significant achievement gaps for sub groups; especially Students with Disabilities and African American populations. The need to continue focus on teacher’s instructional practices based on yearly observation data by the district. Through the objective of “Ensuring success for all students through high quality professional development,” the district is addressing the findings of: The need to improve teachers and administrators understanding of literacy instruction. The need to continue to improve administrator and teachers’ understanding of effective instructional practices- techniques that support Students with Disabilities and African American populations. The need to continue to improve the evaluation and supervision skills of administrators. Through the objective of “Ensuring success for all students through high quality accountability systems,” the district is addressing the findings of: The need to improve the use of data to monitor students’ literacy development K-12. The need to closely monitor teachers and administrators knowledge and skills in implementing the targeted elements in the Educator Rubrics. The need to closely monitor the academic growth of targeted populations (Students with Disabilities and African American students.) LESSONS LEARNED In any model for improvement, there are challenges faced and lessons learned. While some of the activities have already been institutionalized, challenges remain. The district has made significant progress in building the structures and practices that enable consistent, high quality learning for all students. One of the major lessons learned this year became the building block for the 2015 plan: The importance of direct lines of two-way communication with school based educators In the fall of 2013, district leadership struggled with how to effectively communicate the work of the AIP to teachers. The district started by using principals as the primary messengers for the plan’s activities. District leadership soon found that this methodology often resulted in different messages being delivered to different school personnel. This lack of understanding of some AIP initiatives was discovered when the superintendent; assistant superintendent and directors conducted their onsite supervision visits. During these visits, the district leadership found a lack of compliance of agreed upon structures and programs (i.e. The use of Project Read intervention program and SEI instruction during core academic classes). PROCESS FOR DEVELOPING THE 2015 PLAN The institutionalization efforts of the AIP in 2015 began with a collective creation of the 2015 AIP. This plan unlike prior plans, is the work of both the district instructional leadership team and the district’s teachers. The district understands that the success of Randolph students rests solely with the district staff and the future lies with its ability to collectively develop plans focused on improving student achievement and then carefully monitoring the effectiveness of implementation. In the early spring, a team consisting of 52 teachers and administrators (AIP Review and Development Team) led by the district’s Superintendent and Assistant Superintendent, began what was to become a multi-step process to create our fourth year AIP. The process began with the ARDT dividing into eight working groups to reflect on and analyze the work done on our 2013-14 AIP. Each working group’s composition was based on representation from each level; elementary, middle and high school grade spans. To further ensure the credibility and effectiveness of the process, the composition of the working groups were also built around the expertise of the individual members such as having Special Education staff, English Language Learner Staff and counselors focus on initiatives related to their work. Each working group focused on a single initiative. The working groups were first charged with examining the impact of the action steps tied to each initiative. Working groups evaluated district monitoring observation data and student achievement data to determine whether or not each step had achieved its desired outcome, which factors had led to its success and what obstacles had been encountered. Each one of the working groups shared their findings followed by an open discussion with the entire ARDT. Next, the same working groups came together to begin to work on building the new plan and establishing new initiatives, as it had been determined by the ARDT that the time was right for the district to take the work deeper in a continued effort to institutionalize the district’s instructional practices as well as to sustain increased student achievement and growth. To further expand the coalition of support for the 2015 AIP, the Assistant Superintendent conducted a series of listening tours at each school where she solicited input from every teacher. Teachers were asked to reflect on the success of implementation of 2013 AIP along with roadblocks. Teachers were then introduced to the new initiatives developed by the ARDT along with the rationale for each. Lastly, teachers were asked for input on what PD they needed to effectively implement the new initiatives. OVERVIEW OF THE 2015 INITIATIVES While the three objectives from previous years remain consistent, the district has changed the core initiatives in an effort to deepen the work in the district. Closing the achievement gap by strengthening literacy instruction Strengthening core instruction by targeting specific elements in the Educator and Administrator Rubrics: For Teachers: Well Structured Lessons, Adjustment to Practice, Student Enagement, Meeting Diverse Needs. For Administrators: Lesson Development Support, Diverse Learners’ Needs, Observations and Feedback, Alignment Review. Meeting the needs of struggling learners by providing quality tiered instruction, specifically focusing on our students with disabilities and African American populations. Objective 1: Ensuring Success for All Students through High Quality Learning and Teaching For 2014- 2015, the focus is shifting from curriculum development to improving literacy instruction at all grade levels. Key activities for initiative 1.1 include training all staff in Keys to Literacy, designating and training lead teachers and literacy coaches who will provide follow up support with implementation, and the creation of model “literacy’” classrooms for real-time PD experiences for teachers. Under Initiative1.2, the district is shifting from its district developed rubric for instructional practices to one that ties directly to the Educator Evaluation tool. This is being done to strengthen the through-line by linking AIP activities to school improvement and individual teacher performance as measured by the educator evaluation process. Finally, under Initiative1.3, the district is renewing its focus on the tiered system of supports model for all students and with an emphasis on two of the district’s chronically underperforming sub-groups SWD and African Americans. To further enhance the RTSS model the district is looking to strengthen its social and emotional support system by redesigning the practices of the secondary guidance and social work department to be more proactive and data driven. Objective 2: Ensuring Success for All Students through High Quality Professional Development Strategies tied to Objective 2 are designed to support the initiatives in Objective 1 as well as to develop leadership capacity that ultimately results in the institutionalization of the practices in Objective One. The district realizes that it needs to grow its teacher leadership capacity if it is to truly adopt and continue to build upon the work of the 2014 AIP. One of the successes of the 2014 AIP was the district’s ability to create and use teacher leaders and coaches to provide ongoing real-time professional development opportunities for teachers during common planning time periods. The district plans to continue with this methodology along with providing PD around all of the activities in Objective One Objective 3: Ensuring Success for All Students through High Quality Accountability Systems Key to any continuous improvement model is the ability to measure and analyze the results of one’s actions. Therefore, the district will once again focus on measuring the highest points of leverage for improving the performance of administrators and teachers, which will result in improved academic performance for students. The district plans to build upon the measurement tools developed in previous years for collecting qualitative data related to instructional practices, the effectiveness of CPT meetings as well as intervention activities for struggling learners. The one major change for Objective Three is that the district will be switching from the proficiency-based assessments of ANET to the growth-based model offered by NWEA. The district believes that the NWEA MAP assessment and associated RIT scores will provide teachers with the type of data they will need in year four of the plan. Objective 4: Ensuring Success for all Students Through High Quality Engagement Strategies that Support Literacy Development Family engagement is not about increasing family attendance at school events or about even about increasing family interactions with the school, though these may be bi-products of successful engagement activities. Family engagement is about increasing the amount of time parents and guardians invest in rigorous academic interactions with their child as part of a coordinated (family/school) effort to raise their child’s academic performance. There are two strategies that create the keystones for this initiative. The first is to develop family capacity to support rigorous learning at home and the second is to build the capacity of teachers and administrators to be culturally responsive. Family engagement activities will specifically aimed at targeting our students with disabilities and African American populations to provide parents and guardians with tools, skills, and strategies that they can comfortably use to improve their child’s literacy level. A district team is also developing a series of PD activities aimed at building staff’s capacity to effectively communicate with our families and understand the nuances of their students’ cultural backgrounds. 2015 BENCHMARKS The district has decided to change the structure of the AIP benchmarks for 2014-2015. In an effort to clearly delineate the expectations and responsibilities for all educators, in addition to the desired student learning outcomes, the district has developed two areas for the benchmarks: Educator Outcomes and Student Outcomes, Educator Outcomes are designed to monitor the changes in adult behavior. As the district has learned, changes in student outcomes must begin with changes in educator behaviors. By clearly articulating and identifying the desired changes in educator behaviors, the educators in the district will have a clearer understanding of the plan’s expectations for them and how the activities of the plan align student outcomes with changes in their practices. Student Outcomes will have a greater focus on student growth as the NWEA assessment will provide the district and its educators with a tool for measuring both a student’s growth in a subject matter as well as in their literacy level. These two quarterly measurements will provide the district with feedback and evidence on the impact of its initiatives and progress toward accomplishing its objectives. In regards to the benchmarks associated with the high school, because some significant progress was made in these areas the percent of change for some of the benchmarks has been reduced from the 2014 level. The district has created strong systems and must now work to ensure they are being implemented with fidelity across the district. Also, the district must make sure the data systems they are using effectively monitor student progress and bring about teacher ownership for change. The new AIP is much more focused. Creating a system to ensure literacy instruction is aligned throughout the district, focusing intervention on specific targeted groups and aligning principal practice with teacher instructional expectations. THEORY OF ACTION If we align resources, practices, and policies through public engagement to relentlessly focus on the instructional core through student-centered learning at all levels of the district with each person in the organization sharing responsibility for our work, then we will get all students to reach 100% proficiency in their academic, personal and social emotional endeavors. FINAL OUTCOMES The District’s goals are to meet or exceed the PPI target of 75 for 2015 school year and/or meet or exceed the SGP state average for math and ELA.

# Section 2: Plan Summary

| Strategic Objective 1: Ensuring Success for All Students Through High Quality Teaching and Learning |
| --- |
| Strategic Initiatives | Educator and Student Outcomes |
| 1. Closing the achievement gap by strengthening literacy Instruction 2. Strengthen core instruction by focusing on specific elements in the Educator Evaluation Rubrics (For Teachers:Well Structured Lessons, Adjustment to Practice, Student Enagement, Meeting Diverse Needs) (For Administrators Lesson Development Support, Diverse Learners’ Needs, Observations and Feedback, Alignment Review) 3. Meeting the needs of struggling learners by providing quality tiered instruction, specifically for our students with disabilities and African American populations | Educator Outcomes 100% of principals can demonstrate that they have identified their low performing classrooms and are providing support and monitoring progress as evidenced by district leadership’s on site review of principals observation feedback, teacher action plans, and then conducting co observations to the targeted classrooms. By December 1, 100% of core teachers' lesson plans will incorporate the districts new criteria (Mastery Objectives, Engagement Activities, Formative Assessments and Homework as evidenced by building administrators review and assistant superintendent bi-weekly on site review. There will be a 5% increase each quarter (over first quarter baseline) in the number of teachers implementing focused educator evaluation elements as evidenced by district monitoring observation data. By December 1, 100% of principal observation reports will indicate specific feedback on implementation of literacy strategies and educator evaluation elements as evidenced by Assistant Superintendent’s review of reports during bimonthly onsite supervision days. Student Outcomes 75% of all students will reach grade level benchmarks by the end of the year as evidenced by NWEA assessment tool (MAP) in ELA 100% of schools will show a 3% increase (over fall baseline) in their student growth percentile on each administration of the NWEA 70% of students from targeted populations (African American, SWD) will make a minimum of 1.5 years' growth from beginning to end of year as noted by the NWEA assessment tool (MAP) in ELA and Math Data on the HS Principal’s Quarterly Dashboard shows the following changes over base line data from the previous school year: 2% increase each quarter, over same quarter from previous year, in the attendance rate 5% decrease each quarter, over the same quarter from previous year, in the number of suspensions 1.4% decrease each semester, over same semester from previous year, in the number of dropouts 10% decrease each quarter, over same quarter from previous year, in the number of courses failed. 10% decrease, over same quarter from previous year, each quarter in the number of tardies |

| Initiative 1.1 Closing the achievement gap by strengthening literacy instruction |
| --- |
| Activities to Achieve the Outcomes for the Initiative | Who will Lead? | When will it Start? | When will it be Complete? |
| Identify at least two lead teachers from each school who will create model classrooms and provide support for colleagues on effective literacy instruction | Principal | Aug. 2014 | Aug. 2014 |
| Teachers weekly lesson plans will be readily available in classrooms and will include, mastery objective, engagement activities, check for students understanding assessments and homework to be assigned (Elementary core teachers will have available for Math and ELA only) | K-8 Literacy Director | Sept. 2014 | June 2015 |
| CPT will be used to assist K-12 teachers in incorporating Keys to Literacy strategies into lesson plans in all content areas | K-8 Literacy Director | Sept. 2014 | June 2015 |
| Administrators and coaches will observe K-12 teachers implementation of Keys to Literacy strategies in all content areas each month. | K-8 Literacy Director | Sept. 2014 | June 2015 |
| Lead teachers will invite their colleague to observe their literacy instruction | Principal | Sept. 2014 | June 2015 |
| Writing across the curriculum will be stressed (especially in Math and Science) A district math coach will be hired to provide support | Assistant Superintendent | Sept. 2014 | June 2015 |
| Elementary teachers in grades K-4 will use the Wonders (K-4 Lyons Reading Street) program as their primary resource for literacy instruction. Grade 5 teachers will implement a yearlong units aligned to Common Core. | K-8 Literacy Director | Sept. 2014 | June 2015 |
| Literacy coaches will visit classrooms and model lessons | K-8 Literacy Director | Sept. 2014 | June 2015 |
| Complete science pacing guides for K-5 | Assistant Superintendent | Sept. 2014 | June 2015 |
| The district is hiring a data person who will assist administrators’ with collecting monitoring data to assess effectiveness of Tier support systems | Assistant Superintendent | Sept. 2014 | June 2015 |
| Randolph Public Schools will entered into two new partnerships - Bridgewater State College and STAR After School Program - to provide academic support for targeted student populations. | Assistant Superintendent | Sept. 2014 | June 2015 |
| Bridgewater State College and Star Program will train coordinators in the Keys to Literacy Strategies with the expectation that they incorporate these strategies into their lessons and thus, provide continuity between the General Ed, classes and support programs | Assistant Superintendent | Oct. 2014 | June 2015 |

| Initiative 1.2 Strengthen core instruction using specific elements in the Educator Evaluation Rubrics. (For Teachers:Well Structured Lessons, Adjustment to Practice, Student Enagement, Meeting Diverse Needs) (For Administrators Lesson Development Support, Diverse Learners’ Needs, Observations and Feedback, Alignment Review) |
| --- |
| Activities to Achieve the Outcomes for the Initiative | Who will Lead? | When will it Start? | When will it be Complete? |
| Align instructional practice guide with targeted elements in the Educator Evaluation Rubric for Teachers: Well Structured Lessons, Adjustment to Practice, Student Enagement, Meeting Diverse Needs | K-8 Literacy Director | Aug. 2014 | Aug. 2014 |
| Administrators will be orientated to the elements in the administrator rubric that aligned to targeted elements in teacher rubric. [Lesson Development Support, Diverse Learners’ Needs, Observations and Feedback, Alignment Review] District leadership will use rubrics to monitor performance. | Assistant Superintendent | Aug. 2014 | Aug. 2014 |
| Assistant Superintendent will introduce all teachers to the revised instructional practice guide and final AIP at opening day meeting for all staff | Assistant Superintendent | Sept. 2015 | Sept. 2015 |
| Principals will meet monthly with their staffs to revisit expectations for instructional practices using video, modelling instruction and professional readings. | Principal | Sept. 2014 | June 2015 |

| Initiative 1.3 Meeting the needs of struggling learners by providing quality tiered instruction, specifically for our students with disabilities and African American populations |
| --- |
| Activities to Achieve the Outcomes for the Initiative | Who will Lead? | When will it Start? | When will it be Complete? |
| Revise guidelines for K-5 tiered instruction to be more explicit about district expectation that all students have access to grade level curriculum | Assistant Superintendent | Aug. 2015 | Aug. 2015 |
| Establish guidelines for instruction in inclusion classrooms (SPED, ESL and paraprofessional roles) | Special Education Director | Aug. 2015 | Aug. 2015 |
| All principals will develop school schedules that provides adequate time for intervention blocks and submit to assistant superintendent for approval | Principal | Aug. 2015 | Aug. 2015 |
| The District will design a structure for monitoring the instruction and progress of targeted student groups (SWD and African American) | Special Education Director | Aug. 2015 | Sept. 2015 |
| Using OTL protocol, teacher teams will review formative assessments (NWEA, quizzes, unit tests, every six weeks to create/ revise action plans for tiered supports | Assistant Principals | Sept. 2014 | June 2015 |
| Expand use of MA Model for School Counselling to include 6-12 in order to provide complete vertical alignment of tier 1 and tier 2 personal social and college and career readiness interventions | ESSC Coordinator | Sept. 2014 | June 2015 |
| Establish district at-risk indicators for students 6-12 to be used in identifying students in need of support from the social work and guidance department | ESSC Coordinator | Sept. 2014 | June 2015 |
| Guidance/Social Workers will implement a developmental guidance curriculum [incorporating social thinking trainings] K-12 | ESSC Coordinator | Sept. 2014 | June 2015 |
| Guidance/Social Workers will disaggregate social emotional indicators/behaviors to identify at risk students for OTL discussion | ESSC Coordinator | Sept. 2014 | June 2015 |
| Using OTL protocol teacher teams will review student behavior data on a six week cycle to create/ revise action plans for tiered supports | Special Education Director | Sept. 2014 | June 2015 |
| Guidance staff will attend OTL meeting to provide targeted support for students not meeting academic success | Principals | Sept. 2014 | June 2015 |
| Middle School Principal and ELA Director will establish criteria for student entrance into the FLEX reading intervention program for students in grades 6-8 | K-8 Literacy Director | Aug. 2014 | Aug. 2014 |

| Strategic Objective 2: Ensuring Success for All Students Through High Quality Professional Development |
| --- |
| Strategic Initiatives | Educator and Student Outcomes |
| 1. Provide training and support to strengthen literacy instruction 2. Provide training and support to strengthen core instruction using specific elements in the Educator Evaluation Rubrics (For Teachers:Well Structured Lessons, Adjustment to Practice, Student Enagement, Meeting Diverse Needs) (For Administrators Lesson Development Support, Diverse Learners’ Needs, Observations and Feedback, Alignment Review) 3. Provide training and support to ensure all staff are meeting the needs of struggling learners by providing quality tiered instruction, specifically for our students with disabilities and African American populations | Educator Outcomes 100% of principals can demonstrate that they have identified their low performing classrooms and are providing support and monitoring progress as evidenced by district leadership’s on site review of principals observation feedback, teacher action plans, and then conducting co observations to the targeted classrooms. By December 1, 100% of core teachers' lesson plans will incorporate the districts new criteria (Mastery Objectives, Engagement Activities, Formative Assessments and Homework as evidenced by building administrators review and assistant superintendent bi-weekly on site review. There will be a 5% increase each quarter (over first quarter baseline) in the number of teachers implementing focused educator evaluation elements as evidenced by district monitoring observation data. By December 1, 100% of principal observation reports will indicate specific feedback on implementation of literacy strategies and educator evaluation elements as evidenced by Assistant Superintendent’s review of reports during bimonthly onsite supervision days. Student Outcomes 75% of all students will reach grade level benchmarks by the end of the year as evidenced by NWEA assessment tool (MAP) in ELA 100% of schools will show a 3% increase (over fall baseline) in their student growth percentile on each administration of the NWEA 70% of students from targeted populations (African American, SWD) will make a minimum of 1.5 years' growth from beginning to end of year as noted by the NWEA assessment tool (MAP) in ELA and Math Data on the HS Principal’s Quarterly Dashboard shows the following changes over base line data from the previous school year: 2% increase each quarter, over same quarter from previous year, in the attendance rate 5% decrease each quarter, over the same quarter from previous year, in the number of suspensions 1.4% decrease each semester, over same semester from previous year, in the number of dropouts 10% decrease each quarter, over same quarter from previous year, in the number of courses failed. 10% decrease, over same quarter from previous year, each quarter in the number of tardies |

| Initiative 2.1 Provide training and support to strengthen literacy instruction |
| --- |
| Activities to Achieve the Outcomes for the Initiative | Who will Lead? | When will it Start? | When will it be Complete? |
| Develop district and school professional development calendars to support AIP initiatives | Assistant Superintendent | Aug. 2014 | Aug. 2014 |
| Provide Keys to Literacy Coaches Training for all building administrators, directors, lead teachers and coaches | Assistant Superintendent | Aug. 2014 | Aug. 2014 |
| Keys To Literacy Trainer will provide onsite follow up support (6 follow up days) conducting co observing in model classroom with literacy coaches, providing teacher feedback and attending administrator meetings to troubleshoot implementation | Assistant Superintendent | Sept. 2014 | June 2015 |
| Paraprofessionals will participate in all in Keys to Literacy trainings | Assistant Superintendent | Sept. 2014 | June 2015 |
| Provide on-going coaching training to support the implementation of Keys to literacy (BI-Monthly DILT meetings) | Assistant Superintendent | Sept. 2014 | June 2015 |
| Literacy coaches provide on-going professional development in the use of Wonders and Reading Street | K-8 Literacy Director | Sept. 2014 | June 2015 |
| Literacy coaches will provide PD to Teachers on developing lesson plans under new guidelines | K-8 Literacy Director | Sept. 2014 | June 2015 |
| Lead teachers and literacy coaches provide PD during CPT time to support teacher implementation of Keys to Literacy Strategies in all content areas | K-8 Literacy Director | Sept. 2014 | June 2015 |
| Principals will provide time for teachers to observe literacy instruction in model classrooms | Principals | Dec. 2014 | June 2015 |
| Susan Looney, math coach, will provide ongoing support in how to incorporate writing in math classrooms | Assistant Superintendent | Sept. 2014 | June 2015 |

| Initiative 2.2 Provide training and support to strengthen core instruction using specific elements in the Educator Evaluation Rubrics. (For Teachers:Well Structured Lessons, Adjustment to Practice, Student Enagement, Meeting Diverse Needs) (For Administrators Lesson Development Support, Diverse Learners’ Needs, Observations and Feedback, Alignment Review) |
| --- |
| Provide additional training to all building and district administrators on all components of Educator Evaluation System | HR Director | July 2014 | Aug. 2014 |
| Continued PD for administrators on observing instruction and providing effective feedback using targeted elements in the teacher rubric | Assistant Superintendent | Aug 2014 | June 2015 |
| Teachers will be introduced to and receive on-going PD on the targeted elements in the teacher rubric | Principals | Sept. 2014 | June 2015 |
| PD will be provided to all administrators to ensure understanding of the targeted elements in the administrator rubric and how to use to support strengthening core instruction | Assistant Superintendent | Aug. 2014 | June 2015 |
| Conduct monthly school based Learning Walkthroughs (directors and school based personal) to build a shared understanding of district expectations and identify next steps for improving literacy instruction | K-8 Literacy Director | Oct. 2014 | June 2015 |
| All principals will receive coaching support throughout the year | Assistant Superintendent | Sept. 2014 | June 2015 |

| Initiative 2.3 Provide training and support to ensure all staff are meeting the needs of struggling learners by providing quality tiered instruction, specifically for our students with disabilities and African American populations |
| --- |
| Activities to Achieve the Outcomes for the Initiative | Who will Lead? | When will it Start? | When will it be Complete? |
| Provide additional professional development for all administrators on tiered systems of support to ensure effective implementation of Randolph’s revised guide | ELL Director | Aug. 2014 | June 2015 |
| Provide professional development for teachers to ensure understanding of district expectations for tiered systems of supports | ELL Director | Sept. 2014 | June 2015 |
| Provide professional development for administrators and teachers on understanding research best practices in working with targeted groups (SWD and African American) | Director of Family Engagement | Sept. 2014 | June 2015 |
| Provide professional development for guidance and social workers on the MA Model for Comprehensive School Counseling Programs regarding 1)data analysis of at-risk indictors2)the systems that will be used to support students 3) developing guidance curriculum | ESSC Coordinator | Sept. 2014 | June 2015 |
| Provide professional development to all administrators on evidenced based developmental guidance curriculum, including the Social Thinking Framework and college and career readiness. | ESSC Coordinator | Sept. 2014 | June 2015 |
| Provide professional development on the development and implementation of a Developmental Guidance Curriculum to all guidance counselors and social workers | ESSC Coordinator | Sept. 2014 | June 2015 |
| Create a data system to identify disruptive behavior to learning at the secondary level and system of support to respond to decrease behavior. | Director of School Safety | Sept. 2014 | June 2015 |

| Strategic Objective 3: Ensuring Success for All Students Through High Quality Accountability Systems |
| --- |
| Strategic Initiatives | Educator and Student Outcomes |
| 1. Accountability for closing the achievement gap by strengthening literacy instruction 2. Accountability for strengthening core instruction by focusing on specific elements in the Educator Evaluation Rubrics. (For Teachers:Well Structured Lessons, Adjustment to Practice, Student Enagement, Meeting Diverse Needs) (For Administrators Lesson Development Support, Diverse Learners’ Needs, Observations and Feedback, Alignment Review) 3. Accountability of systems for meeting the needs of struggling learners by providing quality tiered instruction, specifically for our students with disabilities and African American populations | Educator Outcomes 100% of principals can demonstrate that they have identified their low performing classrooms and are providing support and monitoring progress as evidenced by district leadership’s on site review of principals observation feedback, teacher action plans, and then conducting co observations to the targeted classrooms. By December 1, 100% of core teachers' lesson plans will incorporate the districts new criteria (Mastery Objectives, Engagement Activities, Formative Assessments and Homework as evidenced by building administrators review and assistant superintendent bi-weekly on site review. There will be a 5% increase each quarter (over first quarter baseline) in the number of teachers implementing focused educator evaluation elements as evidenced by district monitoring observation data. By December 1, 100% of principal observation reports will indicate specific feedback on implementation of literacy strategies and educator evaluation elements as evidenced by Assistant Superintendent’s review of reports during bimonthly onsite supervision days. Student Outcomes 75% of all students will reach grade level benchmarks by the end of the year as evidenced by NWEA assessment tool (MAP) in ELA 100% of schools will show a 3% increase (over fall baseline) in their student growth percentile on each administration of the NWEA 70% of students from targeted populations (African American, SWD) will make a minimum of 1.5 years' growth from beginning to end of year as noted by the NWEA assessment tool (MAP) in ELA and Math Data on the HS Principal’s Quarterly Dashboard shows the following changes over base line data from the previous school year: 2% increase each quarter, over same quarter from previous year, in the attendance rate 5% decrease each quarter, over the same quarter from previous year, in the number of suspensions 1.4% decrease each semester, over same semester from previous year, in the number of dropouts 10% decrease each quarter, over same quarter from previous year, in the number of courses failed. 10% decrease, over same quarter from previous year, each quarter in the number of tardies |

| Initiative 3.1 Accountability for closing the achievement gap by strengthening literacy instruction |
| --- |
| Activities to Achieve the Outcomes for the Initiative | Who will Lead? | When will it Start? | When will it be Complete? |
| District will implement NWEA Assessment Program K-12 to measure students’ academic growth throughout the year | Asst. Superintendent | Sept. 2014 | June 2015 |
| Revise procedures and timelines to ensure consistency in Education Evaluation process and provide administrators with written guidelines | HR Director | July 2014 | July 2014 |
| School Based teams will develop and implement School Improvement Plans aligned to 2014-2015 AIP | Superintendent | Sept. 2014 | Oct. 2014 |
| Building administrators will continue to be required to conduct 5 classroom observations a week (seeing every teacher twice a month) | Asst. Superintendent | Sept. 2014 | June 2015 |
| Principals will continue to submit monthly dashboards that include the following data points: classrooms observations, student behavior, attendance, interim assessment results | Asst. Superintendent | Sept. 2014 | June 2015 |

| Superintendent/Asst. Superintendent will continue to conduct bimonthly onsite principal supervision sessions focused on monitoring implementation of the 3 key AIP initiatives Review observation feedback given to teachers and conduct targeted co-observations Review progress monitoring data and progress of targeted students Visit model literacy classrooms Attending CPT and OTL and reviewing agendas/minutes and action plans for providing tiered supports | Asst. Superintendent | Sept. 2014 | June 2015 |
| --- | --- | --- | --- |
| Asst. Superintendent will continue to provide a summary report for each on site visit with commendations and recommendations for next steps | Asst. Superintendent | Sept. 2014 | June 2015 |
| DLT reviews data from, MCAS, ACCESS, interim assessments, Principals Monthly Dashboards and surveys to inform curriculum, instruction revisions and Accelerated Plan revisions if needed | Superintendent | Sept. 2014 | June 2015 |
| Directors’ monthly meeting agenda will include a review of interim assessments and classroom observation | Superintendent |  |  |
| ELA Director will create a progress monitoring tool and system for tracking reading progress of targeted students and effectiveness of tiered 2 intervention | Superintendent | Sept. 2014 | June 2015 |

| Initiative 3.2 Accountability for strengthening core instruction by focusing on specific elements in the Educator Evaluation Rubrics (For Teachers:Well Structured Lessons, Adjustment to Practice, Student Enagement, Meeting Diverse Needs) (For Administrators Lesson Development Support, Diverse Learners’ Needs, Observations and Feedback, Alignment Review) |
| --- |
| Activities to Achieve the Outcomes for the Initiative | Who will Lead? | When will it Start? | When will it be Complete? |
| Building administrators will compare student achievement data with observation data for trends and patterns to identify future observation focus. | Asst. Superintendent | Sept. 2014 | June 2015 |
| Building administrators will conduct focused observations (5 weekly) and provide specific targeted feedback that is aligned to the district’s instructional expectations and student achievement data. | Principals | Sept. 2014 | June 2015 |
| District leadership reviews and provides feedback to principals bi monthly on quality of observation notes and feedback to teachers | Asst. Superintendent | Sept. 2014 | June 2015 |
| The District Classroom Observation Monitoring tool will be revised to align with this year’s four focus elements in the teacher rubric | Asst. Superintendent | July 2014 | Aug. 2014 |
| District teams will conduct classroom monitoring observations (Fall, Winter, Spring) to assess progress in implementing the district’s instructional expectations. | Asst. Superintendent | Oct. 2014 | May 2015 |

| Initiative 3.3 Accountability of systems for meeting the needs of struggling learners by providing quality tiered instruction, specifically for our students with disabilities and african american populations |
| --- |
| Activities to Achieve the Outcomes for the Initiative | Who will Lead? | When will it Start? | When will it be Complete? |
| Building administrators and directors conduct co-observations (6 week cycle) to monitor effectiveness of implementation of RTSS | ELL Director | Sept. 2014 | June 2015 |
| District implements TEACHPOINT to house educator evaluations and observations | Director of Technology | Aug. 2014 | June 2015 |
| Building administrators supervise implementation of action plans and monitor student progress | Principals | Sept. 2014 | June 2015 |
| Building administrators and Directors review progress monitoring data (6 week cycle) to assess effectiveness of tiered interventions | Principals | Sept. 2014 | June 2015 |
| ESSC grant guidance counselors will review K-12 attendance, discipline and protective factor index data to assess the effectiveness of Tiered social-emotional interventions | ESSC Coordinator | Sept. 2014 | June 2015 |

| Strategic Objective 4: Ensuring Success for All Students Throuh High Quality Engagement Strategies that Support Literacy Development |
| --- |
| Strategic Initiatives | Educator and Student Outcomes |
| 1. Develop family capacity to support rigorous learning at home. 2. Build administrator and teacher capacity to engage all families | Educator Outcome 100% of teachers will communicate with targeted families monthly on their students’ progress in reaching their Lexile levels as evidenced by principals’ review of teachers’ communication logs. Short-term Outcome 80% of targeted students whose parents participate in Family Engagement activities will reach grade level proficiency by the end of year. |

| Initiative 4.1 Develop family capacity to support riorous learning at home |
| --- |
| Activities to Achieve the Outcomes for the Initiative | Who will Lead? | When will it Start? | When will it be Complete? |
| Literacy Coaches will be trained to fill the role of family engagement facilitators | Director of FCR | Aug. 2014 | Sept. 2014 |
| Literacy Coaches will continue providing parent literacy tips | Director of FCR | Sept. 2014 | June 2015 |
| Literacy Coaches will provide four parent workshops on literacy | Director of FCR | Oct. 2014 | June 2015 |
| Literacy Coaches will distribute to new families Common Core for ELA (adapted from the Council of Great City Schools) and distribute to families before first Literacy workshop in Nov. | Director of FCR | Sept. 2014 | June 2015 |
| K-5 Literacy workshops will be open to all families. Family Engagement Facilitators will personally reach out to families of targeted students (students reading below level based on DIBELS and DRA) | Director of FCR | Oct. 2014 | June 2015 |
| Gr. 8-9 Academic Support workshops will be offered three times a year to all families. Director of Family and community engagement will personally reach out to families of targeted students (students who do not meet previous grade level reading scores at the beginning of the school year and/or have not met proficiency levels in ELA from the previous year’s MCAS) | Director of FCR | Oct. 2014 | June 2015 |

| Initiative 4.2 Build administrator and teacher capacity to engage all families |
| --- |
| Activities to Achieve the Outcomes for the Initiative | Who will Lead? | When will it Start? | When will it be Complete? |
| Continue to provide Elementary Literacy Coaches to support teachers and parents in developing students as readers | Director of FCR | Sept. 2014 | June 2015 |
| Coaches work develop the literacy workshop for families and plan a calendar of events for families | Director of FCR | Aug. 2014 | Sept. 2015 |
| Director of FCR will work with a team of administrators to create a professional development series on cultural competency that is focused on deepening teachers understanding of the two targeted populations, African American and students with disabilities | Director of FCR | July 2014 | Aug. 2014 |
| Director of ELL and Multicultural parent advisory council will work with a team of administrators and teachers to design and coordinate a professional development series on cultural competency as it relates to targeted populations | ELL Director | Sept. 2014 | June 2015 |
| Building administrators will conduct cultural competency PD at the school level after receiving training from the Director of FCR and her team each month | Director of FCR | Sept. 2014 | June 2015 |
| Develop communication protocol for talking with parents around students behaviour along with parent contact system to make them aware | Director of Security | Sept. 2014 | June 2015 |